## Slide 1
Project Timeline
August
September
October
32
33
34
35
36
37
38
39
40
41
42
Research into prioritised
components of solution
16/08/2024
18/10/2024
Final Demonstration,
Presentation and Handover
Activity
Remark
23/08/2024
Week
Submission of Project
Specifications Report
16/08/2024 - 22/08/2024
2/08/2024
23/08/2024 - 4/10/2024
Initial Client Meeting
Iterative Development of
Solution Components
Implementation of
Solution components
Project Kick off
Documentation of Solution
Components and Report Feedback
Feedback Implementation and
Project Specification Report
Problem Scoping and Solution
Components Prioritisation
Dependent upon time, resources
and skills
Development update with
prototype of some functionalities
12/08/2024 - 16/08/2024
Initial Mock Up/Demonstration
and Feedback
5/08/2024 - 9/08/2024
7/10/2024 - 17/10/2024
Solution Components Research
Documentation and
Identifying Future Work
Final MVP, Feedback
and Handover